## Sheet1
Company Code | Order Type | Plant | Reference Date | System status | Cost Center | WBS element | WBS ord. header | Order | TotalPlnndCosts | Total act.costs | Priority | Planning Plant | Equipment | Description | Functional Loc. | Notification | User status | Entered By | Created On | Res./Purc. req. | Description | ActualStart | Start time | Sched. start | SchedStartTime | Actual start | Bas. start date | Material | Description
PALM | PM01 | 5E02 | 2026-07-08 | REL CSER MACM PRC SETC | 5E02DTR008 |  |  | 200000760154 | 264334 | 0 | 2 | 5E02 | 2000021315 | Truk KB 8645 WC | PALM-5E02-0001-0003 | 200001190341 | PROS | MK021501 | 2026-07-09 | 3 | BENGKEL | 00:00:00 | 07:30:00 | 2026-07-08 | 07:30:00 |  | 2026-07-08 |  | Permintaan Penggantian Ban Truk
PALM | PM01 | 5E13 | 2024-11-04 | REL GMPS MACM PRC SETC | 5E13CAR001 |  |  | 200000650858 | 3500000 | 1750000 | 2 | 5E13 | 2000014498 | Mobil Manajer DA 8425 HC | PALM-5E13-0001-0003 | 200001082238 | PROS | MK131503 | 2024-11-29 | 3 | BENGKEL | 00:00:00 | 07:00:00 | 2024-11-04 | 07:00:00 |  | 2024-11-04 |  | prbkn kend Da 8425 Hc (Error Ext & Mtrl)
PALM | PM01 | 5F01 | 2026-07-03 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS04 |  |  | 200000760937 | 7650000 | 7650000 | 2 | 5F01 | 1000208005 | STRUCTURE EMPTY RAIL TRACK NO. 2 | PALM-5F01-0005-0004-0001-0022 | 200001192530 | PROS | MP011503 | 2026-07-14 | 3 | STRUCTURE EMPTY RAIL TRACK NO. 2 | 08:52:00 | 08:52:00 | 2026-07-03 | 08:52:00 | 2026-07-03 | 2026-07-03 |  | Perbaikan tracklier lori kosong No.2
PALM | PM01 | 5F01 | 2026-07-03 | REL CNF CSER JBFI MSPT PRC SETC | 5F01STAS04 |  |  | 200000761005 | 901872 | 0 | 2 | 5F01 | 1000208015 | GEARMOTOR CAPSTAN FFB NO. 1 | PALM-5F01-0005-0004-0012-0002-0001 | 200001192520 | PROS | MP011503 | 2026-07-14 | 3 | GEARMOTOR CAPSTAN FFB NO. 1 | 08:05:00 | 08:05:00 | 2026-07-03 | 08:05:00 | 2026-07-03 | 2026-07-03 |  | perbaikan elmot kapstan
PALM | PM01 | 5F01 | 2026-07-03 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS09 |  |  | 200000761007 | 428000 | 428000 | 2 | 5F01 | 1000211020 | FAN ASSY FDF BLR NO. 1 | PALM-5F01-0005-0009-0033-0008-0001 | 200001192522 | PROS | MP011503 | 2026-07-14 | 3 | FAN ASSY FDF BLR NO. 1 | 08:14:00 | 08:14:00 | 2026-07-03 | 08:14:00 | 2026-07-03 | 2026-07-03 |  | perbaikan blower FDF
PALM | PM01 | 5F01 | 2026-07-03 | REL CNF CSER JBFI MACM PRC SETC | 5F01STAS06 |  |  | 200000761010 | 195425000 | 0 | 2 | 5F01 | 1000208573 | FRUIT ELEVATOR NO. 3 | PALM-5F01-0005-0006-0003 | 200001192525 | PROS | MP011503 | 2026-07-14 | 3 | FRUIT ELEVATOR NO. 3 | 08:18:00 | 08:18:00 | 2026-07-03 | 08:18:00 | 2026-07-03 | 2026-07-03 |  | Perbaikan Fruit Elevator No.3
PALM | PM01 | 5F01 | 2026-07-03 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS04 |  |  | 200000761012 | 10200000 | 10200000 | 2 | 5F01 | 1000208002 | STRUCTURE EMPTY RAIL TRACK NO. 1 | PALM-5F01-0005-0004-0001-0021 | 200001192527 | PROS | MP011503 | 2026-07-14 | 3 | STRUCTURE EMPTY RAIL TRACK NO. 1 | 08:27:00 | 08:27:00 | 2026-07-03 | 08:27:00 | 2026-07-03 | 2026-07-03 |  | Perbaikan tracklier lori kosong
PALM | PM01 | 5F01 | 2026-07-02 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS05 |  |  | 200000760697 | 6906500 | 6906500 | 2 | 5F01 | 1000208274 | HOISTING CRANE NO. 1 | PALM-5F01-0005-0005-0001 | 200001192252 | PROS | MP011503 | 2026-07-13 | 3 | HOISTING CRANE NO. 1 | 09:46:00 | 09:46:00 | 2026-07-02 | 09:46:00 | 2026-07-02 | 2026-07-02 |  | Perbaikan hoisting crane no.1
PALM | PM01 | 5F01 | 2026-07-02 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS08 |  |  | 200000760698 | 752223 | 752223 | 2 | 5F01 | 1000210463 | FAN BLOWER LTDS I NO. 1 | PALM-5F01-0005-0008-0054-0003 | 200001192253 | PROS | MP011503 | 2026-07-13 | 3 | FAN BLOWER LTDS I NO. 1 | 09:51:00 | 09:51:00 | 2026-07-02 | 09:51:00 | 2026-07-02 | 2026-07-02 |  | Perbaikan Blower FDF
PALM | PM01 | 5F01 | 2026-07-02 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01WLO001 |  |  | 200000760932 | 1299300 | 1299320 | 2 | 5F01 | 2000015518 | Wheel Loader | PALM-5F01-0001-0003 | 200001192375 | PROS | MP011503 | 2026-07-13 | 3 | WORK SHOP | 20:32:00 | 20:32:00 | 2026-07-02 | 20:32:00 | 2026-07-02 | 2026-07-02 |  | perbaikan loader
PALM | PM01 | 5F01 | 2026-07-02 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS08 |  |  | 200000760935 | 350000 | 350000 | 2 | 5F01 | 1000210463 | FAN BLOWER LTDS I NO. 1 | PALM-5F01-0005-0008-0054-0003 | 200001192378 | PROS | MP011503 | 2026-07-13 | 3 | FAN BLOWER LTDS I NO. 1 | 20:37:00 | 20:37:00 | 2026-07-02 | 20:37:00 | 2026-07-02 | 2026-07-02 |  | Perbaikan Blower LTDS
PALM | PM01 | 5F01 | 2026-07-02 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS09 |  |  | 200000761099 | 163464 | 163463 | 2 | 5F01 | 1000211048 | DUST COLLECTOR BOILER NO. 1 | PALM-5F01-0005-0009-0033-0014 | 200001192397 | PROS | MP011503 | 2026-07-13 | 3 | DUST COLLECTOR BOILER NO. 1 | 19:44:00 | 19:44:00 | 2026-07-02 | 19:44:00 | 2026-07-02 | 2026-07-02 |  | Perbaikan dust collector
PALM | PM01 | 5F01 | 2026-07-02 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS04 |  |  | 200000761100 | 3500000 | 3500000 | 2 | 5F01 | 1000208002 | STRUCTURE EMPTY RAIL TRACK NO. 1 | PALM-5F01-0005-0004-0001-0021 | 200001192398 | PROS | MP011503 | 2026-07-13 | 3 | STRUCTURE EMPTY RAIL TRACK NO. 1 | 19:49:00 | 19:49:00 | 2026-07-02 | 19:49:00 | 2026-07-02 | 2026-07-02 |  | Perbaikan tracklier lori kosong
PALM | PM01 | 5F01 | 2026-07-02 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS08 |  |  | 200000761101 | 4733664 | 4733664 | 2 | 5F01 | 1000210107 | FIBER CYCLONE NO. 1 | PALM-5F01-0005-0008-0005-0005 | 200001192399 | PROS | MP011503 | 2026-07-13 | 3 | FIBER CYCLONE NO. 1 | 19:56:00 | 19:56:00 | 2026-07-02 | 19:56:00 | 2026-07-02 | 2026-07-02 |  | perbaikan fiber cyclone
PALM | PM01 | 5F01 | 2026-07-02 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS10 |  |  | 200000761102 | 134180 | 134180 | 2 | 5F01 | 1000211903 | ANION EXCHANGER NO. 1 | PALM-5F01-0005-0010-0073 | 200001192470 | PROS | MP011503 | 2026-07-13 | 3 | ANION EXCHANGER NO. 1 | 20:02:00 | 20:02:00 | 2026-07-02 | 20:02:00 | 2026-07-02 | 2026-07-02 |  | Perbaikan pump anion cation
PALM | PM01 | 5F01 | 2026-07-01 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS06 |  |  | 200000760689 | 6701158 | 6701158 | 2 | 5F01 | 1000208826 | SCREW PRESS NO. 1 | PALM-5F01-0005-0006-0021 | 200001192034 | PROS | MP011503 | 2026-07-13 | 3 | SCREW PRESS NO. 1 | 09:02:00 | 09:02:00 | 2026-07-01 | 09:02:00 | 2026-07-01 | 2026-07-01 |  | Perbaikan Pressan no.1
PALM | PM01 | 5F01 | 2026-07-01 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS05 |  |  | 200000760690 | 2252666 | 2252667 | 2 | 5F01 | 1000208307 | HOISTING CRANE NO. 2 | PALM-5F01-0005-0005-0002 | 200001192035 | PROS | MP011503 | 2026-07-13 | 3 | HOISTING CRANE NO. 2 | 09:09:00 | 09:09:00 | 2026-07-01 | 09:09:00 | 2026-07-01 | 2026-07-01 |  | Perbaikan hoisting crane no.2
PALM | PM01 | 5F01 | 2026-07-01 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS06 |  |  | 200000760691 | 835310 | 835307 | 2 | 5F01 | 1000208704 | DIGESTER NO. 2 | PALM-5F01-0005-0006-0014 | 200001192036 | PROS | MP011503 | 2026-07-13 | 3 | DIGESTER NO. 2 | 09:14:00 | 09:14:00 | 2026-07-01 | 09:14:00 | 2026-07-01 | 2026-07-01 |  | perbaikan digester no.2
PALM | PM01 | 5F01 | 2026-07-01 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS06 |  |  | 200000760692 | 24399040 | 24399095 | 2 | 5F01 | 1000208826 | SCREW PRESS NO. 1 | PALM-5F01-0005-0006-0021 | 200001192037 | PROS | MP011503 | 2026-07-13 | 3 | SCREW PRESS NO. 1 | 09:18:00 | 09:18:00 | 2026-07-01 | 09:18:00 | 2026-07-01 | 2026-07-01 |  | Perbaikan Pressan no.1
PALM | PM01 | 5F01 | 2026-07-01 | REL CNF CSER JBFI MSPT PRC SETC | 5F01STAS07 |  |  | 200000760693 | 1432340 | 0 | 1 | 5F01 | 1000209636 | DECANTER NO. 1 | PALM-5F01-0005-0007-0098 | 200001192038 | PROS | MP011503 | 2026-07-13 | 3 | DECANTER NO. 1 | 09:23:00 | 09:23:00 | 2026-07-01 | 09:23:00 | 2026-07-01 | 2026-07-01 |  | perbaikan decanter
PALM | PM01 | 5F01 | 2026-07-01 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS05 |  |  | 200000760694 | 7605000 | 7605000 | 2 | 5F01 | 1000208519 | BOTTOM CROSS CONVEYOR NO. 1 | PALM-5F01-0005-0005-0031 | 200001192039 | PROS | MP011503 | 2026-07-13 | 3 | BOTTOM CROSS CONVEYOR NO. 1 | 09:26:00 | 09:26:00 | 2026-07-01 | 09:26:00 | 2026-07-01 | 2026-07-01 |  | perbaikan bottom cross no.1
PALM | PM01 | 5F01 | 2026-07-01 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS06 |  |  | 200000760695 | 5070000 | 5070000 | 2 | 5F01 | 1000208591 | TOP CROSS CONVEYOR NO. 1 | PALM-5F01-0005-0006-0007 | 200001192250 | PROS | MP011503 | 2026-07-13 | 3 | TOP CROSS CONVEYOR NO. 1 | 09:30:00 | 09:30:00 | 2026-07-01 | 09:30:00 | 2026-07-01 | 2026-07-01 |  | perbaikan top cross
PALM | PM01 | 5F01 | 2026-07-01 | REL CNF CSER GMPS JBFI MACM PRC SETC | 5F01STAS07 |  |  | 200000760696 | 5616980 | 5616980 | 1 | 5F01 | 1000209920 | SLUDGE VIBRATING SCREEN NO. 1 | PALM-5F01-0005-0007-0157 | 200001192251 | PROS | MP011503 | 2026-07-13 | 3 | SLUDGE VIBRATING SCREEN NO. 1 | 09:44:00 | 09:44:00 | 2026-07-01 | 09:44:00 | 2026-07-01 | 2026-07-01 |  | Perbaikan Vibro
PALM | PM01 | 5F08 | 2026-07-13 | REL NMAT PRC SETC | 5F08STAS03 |  |  | 200000761082 | 796530100 | 0 | 1 | 5F08 | 1000180548 | BODY HORIZONTAL STERILIZER NO. 2 | PALM-5F08-0005-0003-0002-0001 | 200001192435 | PROS | MP081504 | 2026-07-13 | 3 | BODY HORIZONTAL STERILIZER NO. 2 | 00:00:00 | 07:42:00 | 2026-07-13 | 07:42:00 |  | 2026-07-13 |  | Penggantian Slite Plate Rebusan no.01 02
PALM | PM01 | 5F09 | 2026-07-17 | CRTD NMAT PRC | 5F09STAS06 |  |  | 200000761883 | 0 | 0 | 2 | 5F09 | 1000189288 | FRUIT DISTRIBUTING CONVEYOR NO. 1 | PALM-5F09-0005-0006-0009 | 200001193325 | PLAN | MP091503 | 2026-07-17 | 2 | FRUIT DISTRIBUTING CONVEYOR NO. 1 | 00:00:00 | 10:50:00 | 2026-07-17 | 10:50:00 |  | 2026-07-17 |  | Mengulung Motoran 1KW=1,34/15KW=20
PALM | PM01 | 5F09 | 2026-07-13 | REL CSER GMPS MACM PRC SETC | 5F09EXC001 |  |  | 200000761449 | 516190 | 516190 | 2 | 5F09 | 2000015555 | Excavator Liu Gog PC 75 | PALM-5F09-0001-0003 | 200001193012 | PROS | MP091503 | 2026-07-16 | 3 | WORK SHOP | 00:00:00 | 09:05:00 | 2026-07-13 | 09:05:00 |  | 2026-07-13 |  | Service Excavator
PALM | PM01 | 5F09 | 2026-07-11 | REL CSER GMPS MACM PRC SETC | 5F09STAS09 |  |  | 200000761390 | 57132 | 57132 | 2 | 5F09 | 1000191870 | INCLINED FUEL CONVEYOR BOILER NO. 1 | PALM-5F09-0005-0009-0009 | 200001192891 | PROS | MP091503 | 2026-07-16 | 3 | INCLINED FUEL CONVEYOR BOILER NO. 1 | 00:00:00 | 10:00:00 | 2026-07-11 | 10:00:00 |  | 2026-07-11 |  | Perbaikan Conveyor Sampah Boiler no.1
PALM | PM01 | 5F09 | 2026-07-10 | REL CSER GMPS MACM PRC SETC | 5F09STAS06 |  |  | 200000761524 | 104750 | 104750 | 2 | 5F09 | 1000189521 | SCREW PRESS NO. 3 | PALM-5F09-0005-0006-0023 | 200001192974 | PROS | MP091503 | 2026-07-16 | 3 | SCREW PRESS NO. 3 | 00:00:00 | 08:54:00 | 2026-07-10 | 08:54:00 |  | 2026-07-10 |  | Perbaikan Pressan no.3
PALM | PM01 | 5F09 | 2026-07-09 | REL CSER GMPS MACM PRC SETC | 5F09STAS09 |  |  | 200000760569 | 34650 | 34650 | 2 | 5F09 | 1000191870 | INCLINED FUEL CONVEYOR BOILER NO. 1 | PALM-5F09-0005-0009-0009 | 200001191967 | PROS | MP091503 | 2026-07-11 | 3 | INCLINED FUEL CONVEYOR BOILER NO. 1 | 00:00:00 | 09:32:00 | 2026-07-09 | 09:32:00 |  | 2026-07-09 |  | Perbaikan Inclined FCB nomor 1
PALM | PM01 | 5F09 | 2026-07-08 | REL CSER GMPS MACM PRC SETC | 5F09STAS14 |  |  | 200000760568 | 794900 | 794900 | 2 | 5F09 | 1000194818 | GEARBOX EMPTY BUNCH PRESS NO. 1 | PALM-5F09-0005-0014-0012-0003-0003 | 200001191966 | PROS | MP091503 | 2026-07-11 | 3 | GEARBOX EMPTY BUNCH PRESS NO. 1 | 00:00:00 | 09:23:00 | 2026-07-08 | 09:23:00 |  | 2026-07-08 |  | Gearbox EBP Nomor 1
PALM | PM01 | 5F09 | 2026-07-08 | REL CSER NMAT PRC SETC | 5F09STAS07 |  |  | 200000761737 | 2587500 | 0 | 2 | 5F09 | 1000189722 | CRUDE OIL TANK PUMP NO. 1 | PALM-5F09-0005-0007-0016 | 200001193239 | PROS | MP091503 | 2026-07-17 | 3 | CRUDE OIL TANK PUMP NO. 1 | 00:00:00 | 08:06:00 | 2026-07-08 | 08:06:00 |  | 2026-07-08 |  | Mengulung Motoran 1KW=1,34/5,5 KW=7,5
PALM | PM01 | 5F09 | 2026-07-08 | REL CSER NMAT PRC SETC | 5F09STAS10 |  |  | 200000761738 | 6050000 | 0 | 2 | 5F09 | 1000192395 | WATER INTAKE PUMP NO. 1 | PALM-5F09-0005-0010-0015 | 200001193320 | PROS | MP091503 | 2026-07-17 | 3 | WATER INTAKE PUMP NO. 1 | 00:00:00 | 07:24:00 | 2026-07-08 | 07:24:00 |  | 2026-07-08 |  | Mengulung Motoran 1KW=1,34/18,65KW=25
PALM | PM01 | 5F09 | 2026-07-08 | REL CSER NMAT PRC SETC | 5F09STAS06 |  |  | 200000761879 | 19360000 | 0 | 2 | 5F09 | 1000189433 | SCREW PRESS NO. 1 | PALM-5F09-0005-0006-0021 | 200001193321 | PROS | MP091503 | 2026-07-17 | 3 | SCREW PRESS NO. 1 | 00:00:00 | 10:33:00 | 2026-07-08 | 10:33:00 |  | 2026-07-08 |  | Mengulung Motoran 1KW=1,34/30KW=40
PALM | PM01 | 5F09 | 2026-07-08 | REL CSER NMAT PRC SETC | 5F09STAS08 |  |  | 200000761880 | 1485000 | 0 | 2 | 5F09 | 1000191462 | WET KERNEL CONVEYOR NO. 1 | PALM-5F09-0005-0008-0066 | 200001193322 | PROS | MP091503 | 2026-07-17 | 3 | WET KERNEL CONVEYOR NO. 1 | 00:00:00 | 10:42:00 | 2026-07-08 | 10:42:00 |  | 2026-07-08 |  | Mengulung Motoran 1KW=1,34/2,2 KW=3
PALM | PM01 | 5F09 | 2026-07-08 | REL CSER NMAT PRC SETC | 5F09STAS14 |  |  | 200000761886 | 4840000 | 0 | 2 | 5F09 | 1000194755 | INCLINED EMPTY BUNCH CONVEYOR NO. 1 | PALM-5F09-0005-0014-0004 | 200001193328 | PROS | MP091503 | 2026-07-17 | 3 | INCLINED EMPTY BUNCH CONVEYOR NO. 1 | 00:00:00 | 10:54:00 | 2026-07-08 | 10:54:00 |  | 2026-07-08 |  | Mengulung Motoran 1KW=1,34/15KW=20
PALM | PM01 | 5F09 | 2026-07-07 | REL CSER GMPS MACM PRC SETC | 5F09STAS09 |  |  | 200000760566 | 169385 | 169383 | 2 | 5F09 | 1000191969 | BOILER NO. 1 | PALM-5F09-0005-0009-0033 | 200001191964 | PROS | MP091503 | 2026-07-11 | 3 | BOILER NO. 1 | 00:00:00 | 09:08:00 | 2026-07-07 | 09:08:00 |  | 2026-07-07 |  | Perbaikan boiler no 1
PALM | PM01 | 5F09 | 2026-07-07 | REL CSER GMPS MACM PRC SETC | 5F09STAS07 |  |  | 200000760567 | 790000 | 790000 | 2 | 5F09 | 1000189978 | VACUUM PUMP NO. 1 VACUUM OIL DRYER NO. 1 | PALM-5F09-0005-0007-0058-0003 | 200001191965 | PROS | MP091503 | 2026-07-11 | 3 | VACUUM PUMP NO. 1 VACUUM OIL DRYER NO. 1 | 00:00:00 | 08:16:00 | 2026-07-07 | 08:16:00 |  | 2026-07-07 |  | Pompa Vacum no 1
PALM | PM01 | 5F09 | 2026-07-06 | REL CSER GMPS MACM PRC SETC | 5F09STAS09 |  |  | 200000761248 | 265200 | 265200 | 2 | 5F09 | 1000192084 | AIR PREHEATER BOILER NO. 2 | PALM-5F09-0005-0009-0034-0003 | 200001192663 | PROS | MP091503 | 2026-07-14 | 3 | AIR PREHEATER BOILER NO. 2 | 00:00:00 | 08:04:00 | 2026-07-06 | 08:04:00 |  | 2026-07-06 |  | Perbaikan Boiler no.2
PALM | PM01 | 5F09 | 2026-07-06 | REL CSER GMPS MACM PRC SETC | 5F09STAS06 |  |  | 200000761623 | 320525 | 320523 | 2 | 5F09 | 1000189433 | SCREW PRESS NO. 1 | PALM-5F09-0005-0006-0021 | 200001193045 | PROS | MP091503 | 2026-07-17 | 3 | SCREW PRESS NO. 1 | 00:00:00 | 08:29:00 | 2026-07-06 | 08:29:00 |  | 2026-07-06 |  | Perbaikan Pressan No.1
PALM | PM01 | 5F09 | 2026-07-04 | REL CSER GMPS MACM PRC SETC | 5F09STAS06 |  |  | 200000761089 | 1587020 | 1587020 | 2 | 5F09 | 1000189441 | GEARBOX SCREW PRESS NO. 1 | PALM-5F09-0005-0006-0021-0002-0002 | 200001192652 | PROS | MP091503 | 2026-07-14 | 3 | GEARBOX SCREW PRESS NO. 1 | 00:00:00 | 07:49:00 | 2026-07-04 | 07:49:00 |  | 2026-07-04 |  | Perbaikan Gearbox Pressan no.1
PALM | PM01 | 5F09 | 2026-07-04 | CRTD NMAT PRC | 5F09STAS07 |  |  | 200000761736 | 0 | 0 | 2 | 5F09 | 1000189722 | CRUDE OIL TANK PUMP NO. 1 | PALM-5F09-0005-0007-0016 | 200001193238 | PLAN | MP091503 | 2026-07-17 | 2 | CRUDE OIL TANK PUMP NO. 1 | 00:00:00 | 08:02:00 | 2026-07-04 | 08:02:00 |  | 2026-07-04 |  | Mengulung Motoran 1KW=1,34/5,5 KW=7,5
PALM | PM01 | 5F09 | 2026-07-02 | REL CSER GMPS MACM PRC SETC | 5F09STAS05 |  |  | 200000760565 | 487085 | 487083 | 2 | 5F09 | 1000189036 | THRESHER DRUM NO. 3 | PALM-5F09-0005-0005-0019 | 200001191963 | PROS | MP091503 | 2026-07-11 | 3 | THRESHER DRUM NO. 3 | 00:00:00 | 08:58:00 | 2026-07-02 | 08:58:00 |  | 2026-07-02 |  | Perbaikan Threser No .3
PALM | PM01 | 5F09 | 2026-07-01 | REL CSER GMPS MACM PRC SETC | 5F09STAS06 |  |  | 200000761251 | 1024000 | 1024000 | 2 | 5F09 | 1000189252 | GEARMOTOR FRUIT ELEVATOR NO. 3 | PALM-5F09-0005-0006-0003-0003-0001 | 200001192666 | PROS | MP091503 | 2026-07-14 | 3 | GEARMOTOR FRUIT ELEVATOR NO. 3 | 00:00:00 | 07:16:00 | 2026-07-01 | 07:16:00 |  | 2026-07-01 |  | Pelumas Grease Gearmotor fruit elevator3
PALM | PM01 | 5F09 | 2026-06-19 | REL NMAT PRC SETC | 5F09STAS08 |  |  | 200000755460 | 44737500 | 0 | 2 | 5F09 | 1000191407 | CLAYBATH NO. 1 | PALM-5F09-0005-0008-0062 | 200001183692 | PROS | MP091503 | 2026-06-19 | 3 | CLAYBATH NO. 1 | 00:00:00 | 14:01:00 | 2026-06-19 | 14:01:00 |  | 2026-06-19 |  | REKONDISI VIBRATING CLAYBATH
PALM | PM01 | 5F09 | 2026-06-19 | REL GMPS NMAT PRC SETC | 5F09STAS07 |  |  | 200000755461 | 16500000 | 16500000 | 2 | 5F09 | 1000190609 | SLUDGE SEPARATOR NO. 3 | PALM-5F09-0005-0007-0147 | 200001183693 | PROS | MP091503 | 2026-06-19 | 3 | SLUDGE SEPARATOR NO. 3 | 00:00:00 | 14:37:00 | 2026-06-19 | 14:37:00 |  | 2026-06-19 |  | PERBAIKAN 1 UNIT SLUDGE SEPARATOR PASX
PALM | PM01 | 5F15 | 2026-07-13 | REL NMAT PRC SETC | 5F15STAS11 |  |  | 200000760963 | 0 | 0 | 2 | 5F15 | 1000199243 | DIESEL GENERATING SET NO. 1 | PALM-5F15-0005-0011-0007 | 200001192331 | PROS | MP151501 | 2026-07-13 | 3 | DIESEL GENERATING SET NO. 1 | 00:00:00 | 11:05:00 | 2026-07-13 | 11:05:00 |  | 2026-07-13 |  | Penggantian Accu Genset No 1
PALM | PM01 | 5F15 | 2026-07-13 | REL GMPS MACM PRC SETC | 5F15STAS11 |  |  | 200000760967 | 7000000 | 7000000 | 2 | 5F15 | 1000199243 | DIESEL GENERATING SET NO. 1 | PALM-5F15-0005-0011-0007 | 200001192335 | PROS | MP151501 | 2026-07-13 | 3 | DIESEL GENERATING SET NO. 1 | 00:00:00 | 11:15:00 | 2026-07-13 | 11:15:15 |  | 2026-07-13 |  | Penggantian Accu Genset No 1
PALM | PM01 | 5F15 | 2026-07-13 | REL GMPS MACM PRC SETC | 5F15STAS03 |  |  | 200000760970 | 9193225 | 9193226 | 2 | 5F15 | 1000195343 | CONDENSATE PIT | PALM-5F15-0005-0003-0015 | 200001192338 | PROS | MP151501 | 2026-07-13 | 3 | CONDENSATE PIT | 00:00:00 | 11:25:00 | 2026-07-13 | 11:25:00 |  | 2026-07-13 |  | Pengelasan Pipa Kondensat Rebusan
PALM | PM01 | 5F15 | 2026-07-13 | REL MACM PRC SETC | 5F15STAS09 |  |  | 200000760975 | 177708 | 0 | 2 | 5F15 | 1000198243 | PUMP ASSY ELEC MOTOR DRV WTR PUMP NO. 2 | PALM-5F15-0005-0009-0018-0001 | 200001192383 | PROS | MP151501 | 2026-07-13 | 3 | PUMP ASSY ELEC MOTOR DRV WTR PUMP NO. 2 | 00:00:00 | 14:04:00 | 2026-07-13 | 14:04:00 |  | 2026-07-13 |  | Penggantian Bearing ElektrikPump Boiler
PALM | PM01 | 5F15 | 2026-07-13 | REL MACM PRC SETC | 5F15STAS07 |  |  | 200000760976 | 3772066 | 0 | 2 | 5F15 | 1000197214 | SLUDGE CENTRIFUGE NO. 1 | PALM-5F15-0005-0007-0178 | 200001192384 | PROS | MP151501 | 2026-07-13 | 3 | SLUDGE CENTRIFUGE NO. 1 | 00:00:00 | 14:15:00 | 2026-07-13 | 14:15:00 |  | 2026-07-13 |  | Penggantian Bearing Centrifuge No 1
PALM | PM02 | 5F15 | 2026-07-07 | REL NMAT PRC SETC | 5F15STAS14 |  |  | 210000336704 | 0 | 0 | 3 | 5F15 | 1000199881 | EMPTY BUNCH PRESS NO. 1 | PALM-5F15-0005-0014-0012 | 200001189684 | PROS | IP1020260703 | 2026-07-03 | 3 | EMPTY BUNCH PRESS NO. 1 | 00:00:00 | 00:00:00 | 2026-07-07 | 00:00:00 |  | 2026-07-07 |  | 5F15 PREVENTIVE BUNCH PRESS 600 HM
PALM | PM01 | 5F15 | 2026-06-19 | REL NMAT PRC SETC | 5F15STAS07 |  |  | 200000755329 | 2310000 | 0 | 2 | 5F15 | 1000196107 | ELECTROMOTOR VIBRATING SCREEN NO. 1 | PALM-5F15-0005-0007-0005-0003 | 200001183704 | PROS | MP151501 | 2026-06-19 | 3 | ELECTROMOTOR VIBRATING SCREEN NO. 1 | 00:00:00 | 14:07:00 | 2026-06-19 | 14:07:00 |  | 2026-06-19 |  | Perbaikan Gulung Ulang Elektro Motor
PALM | PM04 | 5F15 | 2026-06-19 | REL NMAT PRC SETC | 5F15STAS08 |  | PC-26-5F15-05-27-03 | 230000018873 | 327908400 | 0 | 1 | 5F15 | 1000197313 | FIBER CYCLONE NO. 1 | PALM-5F15-0005-0008-0005-0005 |  | PROS | MP151501 | 2026-06-19 | 3 | FIBER CYCLONE NO. 1 | 00:00:00 | 14:55:00 | 2026-06-19 | 14:55:00 |  | 2026-06-19 |  | Penggantian Ducting Fiber Cyclone
PALM | PM02 | 5F22 | 2026-07-22 | REL NMAT PRC SETC | 5F22STAS06 |  |  | 210000338655 | 0 | 0 | 3 | 5F22 | 1000174275 | SCREW PRESS NO. 3 | PALM-5F22-0005-0006-0023 | 200001192948 | PROS | IP1020260716 | 2026-07-16 | 3 | SCREW PRESS NO. 3 | 00:00:00 | 00:00:00 | 2026-07-22 | 00:00:00 |  | 2026-07-22 |  | 5F22 PREVENTIVE SCREW PRESS 1200 HM
PALM | PM01 | 5F22 | 2026-07-17 | REL CSER MACM PRC SETC | 5F22STAS03 |  |  | 200000761730 | 17948800 | 0 | 2 | 5F22 | 1000171459 | STRUCTURE AND CATWALK STERILIZER STATION | PALM-5F22-0005-0003-0013 | 200001193232 | PROS | MP221503 | 2026-07-17 | 3 | STRUCTURE AND CATWALK STERILIZER STATION | 00:00:00 | 08:00:00 | 2026-07-17 | 08:00:00 |  | 2026-07-17 |  | besi siku jembatan rebusan
PALM | PM01 | 5F22 | 2026-07-17 | REL CSER MACM PRC SETC | 5F22STAS05 |  |  | 200000761732 | 3010400 | 0 | 2 | 5F22 | 1000173482 | AUTOFEEDER NO. 2 | PALM-5F22-0005-0005-0014 | 200001193234 | PROS | MP221503 | 2026-07-17 | 3 | AUTOFEEDER NO. 2 | 00:00:00 | 08:00:00 | 2026-07-17 | 08:00:00 |  | 2026-07-17 |  | besi siku auto fetder
PALM | PM01 | 5F22 | 2026-07-17 | REL CSER MACM PRC SETC | 5F22STAS05 |  |  | 200000761734 | 2016400 | 0 | 2 | 5F22 | 1000173584 | STRUCTURE THRESHER DRUM NO. 2 | PALM-5F22-0005-0005-0018-0004 | 200001193236 | PROS | MP221503 | 2026-07-17 | 3 | STRUCTURE THRESHER DRUM NO. 2 | 00:00:00 | 08:00:00 | 2026-07-17 | 08:00:00 |  | 2026-07-17 |  | besi siku
PALM | PM01 | 5F22 | 2026-07-17 | REL CSER MACM PRC SETC | 5F22STAS05 |  |  | 200000761735 | 2357200 | 0 | 2 | 5F22 | 1000173744 | STRUCTURE BOTTOM CROSS CONVEYOR NO. 1 | PALM-5F22-0005-0005-0031-0004 | 200001193237 | PROS | MP221503 | 2026-07-17 | 3 | STRUCTURE BOTTOM CROSS CONVEYOR NO. 1 | 00:00:00 | 08:00:00 | 2026-07-17 | 08:00:00 |  | 2026-07-17 |  | besi siku EBC
PALM | PM01 | 5F22 | 2026-07-16 | REL CSER GMPS MACM PRC SETC | 5F22STAS08 |  |  | 200000761539 | 391632 | 391632 | 2 | 5F22 | 1000176589 | FAN BLOWER LTDS II NO. 1 | PALM-5F22-0005-0008-0054-0004 | 200001193000 | PROS | MP221503 | 2026-07-16 | 3 | FAN BLOWER LTDS II NO. 1 | 00:00:00 | 08:00:00 | 2026-07-16 | 08:00:00 |  | 2026-07-16 |  | Adapter bearing LTDS no. 2 line 1
PALM | PM01 | 5F22 | 2026-07-16 | REL CSER GMPS MACM PRC SETC | 5F22STAS08 |  |  | 200000761540 | 1906340 | 1906341 | 2 | 5F22 | 1000176589 | FAN BLOWER LTDS II NO. 1 | PALM-5F22-0005-0008-0054-0004 | 200001193001 | PROS | MP221503 | 2026-07-16 | 3 | FAN BLOWER LTDS II NO. 1 | 00:00:00 | 08:00:00 | 2026-07-16 | 08:00:00 |  | 2026-07-16 |  | Bearing Blower LTDS no. 2 line 1
PALM | PM01 | 5F22 | 2026-07-16 | REL CSER GMPS MACM PRC SETC | 5F22STAS08 |  |  | 200000761541 | 1232554 | 1232553 | 2 | 5F22 | 1000176589 | FAN BLOWER LTDS II NO. 1 | PALM-5F22-0005-0008-0054-0004 | 200001193002 | PROS | MP221503 | 2026-07-16 | 3 | FAN BLOWER LTDS II NO. 1 | 00:00:00 | 08:00:00 | 2026-07-16 | 08:00:00 |  | 2026-07-16 |  | Housing Blower LTDS no. 2 line 1
PALM | PM04 | 5F22 | 2026-06-19 | REL NMAT PRC SETC | 5F22STAS08 |  | PC-26-5F22-05-27-01 | 230000019095 | 224971100 | 0 | 2 | 5F22 | 1000176907 | WET KERNEL ELEVATOR NO. 1 | PALM-5F22-0005-0008-0068 |  | PROS | MP221503 | 2026-06-19 | 3 | WET KERNEL ELEVATOR NO. 1 | 00:00:00 | 15:03:00 | 2026-06-19 | 15:03:00 |  | 2026-06-19 |  | rekondisi wet kernel elevator no 1
PALM | PM04 | 5F22 | 2026-06-19 | REL NMAT PRC SETC | 5F22STAS05 |  | PC-26-5F22-05-22-02 | 230000019128 | 180149694 | 0 | 2 | 5F22 | 1000173628 | UNDER THRESHER CONVEYOR NO. 1 | PALM-5F22-0005-0005-0024 |  | PROS | MP221503 | 2026-06-19 | 3 | UNDER THRESHER CONVEYOR NO. 1 | 00:00:00 | 15:47:00 | 2026-06-19 | 15:47:00 |  | 2026-06-19 |  | Penggantian Conveyor Under Thresser no 1
PALM | PM01 | 5F22 | 2025-01-02 | REL PCNF GMPS JIPR MACM PRC SETC | 5F22STAS08 |  |  | 200000661079 | 140000 | 683954 | 2 | 5F22 | 1000094462 | CLAY BATH | PALM-5F22-0002-ST08 | 200001091969 | PROS | MP221503 | 2025-01-02 | 3 | STASIUN PENGOLAHAN INTI SAWIT | 08:00:00 | 08:00:00 | 2025-01-02 | 08:00:00 | 2024-12-31 | 2025-01-02 |  | PERBAIKAN CLYBATH (Err PCOM 2024 Nt Opn)